## Sheet1
NIGHTCAP PRODUCTION – PRODUCER PLAN
	Concept	Animation	Environment	Character	Milestones
Fall Semester
Week 1	Storyboards, Beauty Shots, Character Sheet	Storyboard	downshot of envir, ref library	Rough Model, look and feel	M3: Finalize Story Idea
Week 2	Refine Character and other Designs	2d animatic 1st pass	concept 1st pass	character sheet 2nd pass
Week 3	Refine Character and other Designs	2d animatic 2nd pass	concept 2nd pass	character model	M4: 1st pass 2d animatic
Week 4	Layout, Style guide, Model Sheet, Action Poses	2d animatic final pass	concept final	character model	M5: 2d animatic final w/ Concept, style final, 1st pass color script, 1st pass sound
Week 5	Expression Sheet, color script 1st pass	test body rig, walk, take	shader develop, look and feel	character body rig
Week 6	finalize Expression sheet	facial rig expression test	model 1st pass	character facial rig	M6: Animation test, walk, expressions model / rig review 1st pass
Week 7	Work on final 2 pieces	test rig / camera layout	camera layout, rough block	rig revisions
Week 8	2 pieces character in environment concept final	motion/acting ref	model 2nd pass	finalizing model and rig	M7: 2 pieces, character in environment, concept final
Week 9	Color Script 2nd Pass	animate rig/motion/acting	model 3rd pass	texture 1st pass
Week 10	Work on 2D animation	animate rig/motion/acting	model final pass	texture 2nd pass	M8: Character model, rig, texture, environment, cameras finished
Week 11	1st pass on 2D animation	plan/block animation	envir shaders/ materials	texture final pass
Week 12	2nd pass on 2D animation	blocking animation	envir shaders/ materials	SFX design planning
Week 13	3rd pass on 2D animation	1st pass 3d animatic	render test w/ light, shadow, materials	Sound 1st pass	M9: 1st pass 3d animatic, 1st pass sound
Week 14	Rough Credits / Titles Concept	blocking animation	modify lighting, shadow, materials	Sound revisions
Week 15	finalizing 2D animation	final pass 3d animatic	modify lighting, shadow, materials	Sound / SFX revisions	M10: 3d animatic finished, environment shaders

Spring Semester
Week 1	Revisions on 2D animation	Revised Blocking	Texture large elements	SFX 1st pass
Week 2	Revise Color Script, Specific Lighting Guide	Revised Blocking	finalize large texture elements	SFX editing	M11: Revise blocking final, envrionment large texture finished
Week 3	Revise color script	Spline half of film	texture small elements	SEF editing
Week 4	1st pass Lighting	spline other half	finalize small texture elements	Lighting Editing	M12: Splining, environment small texture finished
Week 5	Editing	polish half of film	1st pass lighting	1st pass lighting half of film
Week 6	2nd pass lighting	polish other half	editing	SFX 2nd pass	M13: 1st pass on Lighting, Animation finished
Week 7	Editing	animation fixes	2nd pass lighting	SFX editing
Week 8	Editing	animation fixes	editing	SFX final	M14: 2nd pass Lighting
Week 9	SPRING BREAK
Week 10	Final lighting	animation fixes	lighting final	Lighting final
Week 11	title/ credit design	Finalize animation	Finish Lighting	2nd pass sound/music	M15: Final lighting, 2nd pass sound/music
Week 12	title/ credit design 1st pass	Render	render	Render
Week 13	title/ credit design final	Render fixes	render fixes	Final sound/music	M16: 1st pass on everything
Week 14	render fixes	render fixes	render fixes	Sound/Music revisions
Week 15	render fixes	Render fixes	render fixes	render	Final Submission

Guide:
Lighting
Animation
Environment
Character
Concept
SFX
Sound
Milestones
Holidays
Render

## Sheet2
NIGHTCAP PRODUCTION – TEAM MEMBER PLANNING SHEET
	Max Engman	Ryan Gates	Erik Miles	Laura Franke	Bret Linne	Milestones
Fall Semester
Week 1	Rough Model, look and feel	Storyboard	downshot of envir, ref library	Storyboards, Beauty Shots, Character Sheet		M3: Finalize Story Idea
Week 2	character sheet 2nd pass	2d animatic 1st pass	concept 1st pass	Refine Character and other Designs	JUST JOINED TEAM
Week 3	Refine Character and other Designs	2D animatic 2nd pass / character model	concept 2nd pass	Refine Character and other Designs	Style guide Background	M4: 1st pass 2d animatic
Week 4	Layout, Style guide, Model Sheet, Action Poses	2D animatic final pass / character model	concept final	Layout, Style guide, Model Sheet, Action Poses	Layout, Style guide, Model Sheet, Action Poses	M5: 2d animatic final w/ Concept, style final, 1st pass color script, 1st pass sound
Week 5	Expression sheet	character body rig	shader develop, look and feel	Expression Sheet, color script 1st pass	Expression Sheet, color script 1st pass
Week 6	finalize Expression sheet	character facial rig	model 1st pass	finalize Expression sheet	finalize Expression sheet	M6: Animation test, walk, expressions model / rig review 1st pass
Week 7	Work on final 2 pieces	rig revisions	Camera Layout, look and feel, Work on final 2 pieces	Work on final 2 pieces	Work on final 2 pieces
Week 8	2 pieces character in environment concept final	finalizing model and rig	model 2nd pass	2 pieces character in environment concept final	2 pieces character in environment concept final	M7: 2 pieces, character in environment, concept final
Week 9	texture 1st pass	animate rig/motion/acting	model 3rd pass	Color Script 2nd Pass	Color Script 2nd Pass
Week 10	texture 2nd pass	animate rig/motion/acting	model final pass	Work on 2D animation	Work on Ending Credits	M8: Character model, rig, texture, environment, cameras finished
Week 11	texture final pass	plan/block animation	envir shaders/ materials	1st pass on 2D animation	1st pass on Ending Credits
Week 12	blocking animation	blocking animation	SFX design planning / envir shaders and materials	2nd pass on 2D animation	2nd pass on Ending Credits
Week 13	1st pass 3d animatic	1st pass 3d animatic	Sound 1st pass / render test w/ light, shadow, materials	3rd pass on 2D animation	3rd pass on Ending Credits	M9: 1st pass 3d animatic, 1st pass sound
Week 14	blocking animation	blocking animation	Sound revisions / modify lighting, shadow, materials	Rough Credits / Titles Concept	Rough Credits / Titles Concept
Week 15	final pass 3d animatic	final pass 3d animatic	Sound / SFX revisions / modify lighting, shaodw, materials	finalizing 2D animation	finalizing Ending Credits	M10: 3d animatic finished, environment shaders

Spring Semester
Week 1	Texture large elements	Revised Blocking	SFX 1st pass / texture large elements	Revisions on 2D animation	Revisions on 2D animation
Week 2	finalize large texture elements	Revised Blocking	SFX editing / finalizing large texture elements	Revise Color Script, Specific Lighting Guide	Revise Color Script, Specific Lighting Guide	M11: Revise blocking final, envrionment large texture finished
Week 3	texture small elements	Spline half of film	SFX editing / texture small elements	Revise color script	Revise color script
Week 4	finalize small texture elements	spline other half	1st pass lighting / finalizing small texture elements	1st pass lighting	1st pass lighting	M12: Splining, environment small texture finished
Week 5	editing	polish half of film	Lighting editing	editing	editing
Week 6	2nd pass lighting	polish other half	SFX 2nd pass / lighting editing	3D character layout	3D character layout	M13: 1st pass on Lighting, Animation finished
Week 7	Editing	animation fixes / lighting editing	SFX editing / lighting editing	Post-Production editing	Post-Production Editing
Week 8	Editing	animation fixes / lighting editing	SFX final / lighting editing	Post-Production editing	Post-Production Editing	M14: 2nd pass Lighting
Week 9	SPRING BREAK
Week 10	Final lighting	animation fixes	Lighting final	Finalizing Post-Production editing	Finalizing Post-Production Editing
Week 11	Finish Lighting	Finalize animation	2nd pass sound/music	Blending 2D to 3D	Blending 2D to 3D	M15: Final lighting, 2nd pass sound/music
Week 12	render	Render	Render	Blending 2D to 3D	Blending 2D to 3D
Week 13	render fixes	Render fixes	Final sound/music	title/ credit design final	title/ credit design final	M16: 1st pass on everything
Week 14	render fixes	render fixes	Sound/Music revisions	render	render
Week 15	render fixes	Render fixes	render	render	render	Final Submission

Guide:
Lighting
Animation
Environment
Character
Concept
SFX
Sound
Milestones
Holidays
Render