## Sheet1
Fall		Concept	animator Schedule	Lighting	Render	Enviornments	FX/Lighting		HOLIDAYS
Spring
1	jan 9-13		1/3 film revised blocking			Texture Blocked Environment	SFX 1st Pass	M0:Excel plan
2	jan 16-20	revise color script, specific lighting guide	1/3 film spline			Texture Environment	SFX 1st Pass		MLK holiday
3	jan 23-27	revise color script	1/3 film polish			Texture Environment		1/3 of film animated. Revised color script.
4	jan 30-feb 3		2/3 film revised blocking	1st Pass Lighting 1/3 film		Texture Final Environment		Environment textures finished/working.
5	feb 6-10		2/3 film spline	2nd Pass Lighting 1/3 film
6	feb 13-17		2/3 film polish		render 1/3 film		SFX 2nd pass	2/3 of film animated. Lighting tests, the “look”. Render composite time tests.
7	feb 20-24		final film revised blocking	1st Pass Lighting 2/3 film	render 1/3 film		SFX 2nd pass	Midterm	President's Day
8	feb27-mar 2		final scene film spline	2nd Pass Lighting 2/3 film			SFX Final	Start of GDC
9	mar 5-9	SPRING BREAK	SPRING BREAK	SPRING BREAK	SPRING BREAK	SPRING BREAK	SPRING BREAK	Spring Break/ GDC	SPRING BREAK
10	mar 12-16	title/credit design	final scene film polish	1st Pass lighting final scenes	render 2/3 film			1/3 of film animated. Final lighting done/working.
11	mar 19-23	title/credit 1st pass	Animation fixes	2nd Pass Lighting final scenes	render 2/3 film		2nd pass sound/music	Must be rendering by now
12	mar 26-30	Career Day	Career Day	Career Day	render final scenes	Career Day	Career Day	Career Day
13	april 2-6	title/credits final			render final scenes		final sound/music	First Pass All scenes rendered Review, Credits Final, final sound
14	april9-13	render fixes			render fixes		revise sound/music		Siggraph Deadline 4/15/2011
15	april 16-20	render fixes			render fixes		render fixes	Revise All scenes rendered Review, Revise Credits Final, Revise final sound
16	april 23-27	Final Film Submission				Final Film Submission	Final Film Submission	Final Film Submission

## Sheet2
SPRING SEMESTER PLANNING – NIGHTCAP
Week	Erik Miles	Bret Linne	Ryan Gates	Max Engman	Rendering	Important Dates	Milestones
1	Char Revi / Texture Blocked Environment	revise color script, specific lighting guide	Char / 1/3 film revised blocking – 4 shots	Texture Env / 1/3 film revised blocking – 4 shots			M0:Excel plan
2	Char Rev / Texture Environment	revise color script	Char / 1/3 film spline – 4 shots	Texture Envi / 1/3 film spline – 4 shots		MLK Holiday – Mon
3	Char Rev / Texture Environment	½ film blocking tentacle	Char / 1/3 film polish – 4 shots	Texture Envi / 1/3 film polish – 4 shots			1/3 of film animated. Revised color script.
4	Final Texture Envir / 1st Pass Lighting 1/3 film	½ film spline tentacle	2/3 film revised blocking – 4 shots	Final Texture / 2/3 film revised blocking – 4 shots			Environment textures finished/working.
5	2nd Pass Lighting 1/3 film	½ film polish tentacle	2/3 film spline – 4 shots	2/3 film spline – 4 shots
6		Light / 2/2 film blocking tentacle	2/3 film polish – 4 shots	2/3 film polish – 4 shots	render 1/3 film		2/3 of film animated. Lighting tests, the “look”. Render composite time tests.
7	1st Pass Lighting 2/3 film	Light / 2/2 film spline tentacle	final film revised blocking – 4 shots	final film revised blocking – 4 shots	render 1/3 film	President Day – Mon	Midterm
8	2nd Pass Lighting 2/3 film	Light / 2/2 film final tentacle	final scene film spline – 4 shots	final scene film spline – 4 shots			Start of GDC
9	Spring Break					Spring Break/ GDC
10	1st Pass lighting final scenes	title/credit design	final scene film polish	final scene film polish	render 2/3 film		1/3 of film animated. Final lighting done/working.
11	2nd Pass Lighting final scenes / 2nd pass sound	title/credit 1st pass	Animation fixes	Animation fixes	render 2/3 film		Must be rendering by now
12	Career Day				render final scenes	Career Day
13	final sound/music	Render Fixes	Render Fixes	Render Fixes	render final scenes		First Pass All scenes rendered Review, Credits Final, final sound
14	revise sound/music	Render Fixes	Render Fixes	Render Fixes		Siggraph Deadline
15	Render Fixes	Render Fixes	Render Fixes	Render Fixes			Revise All scenes rendered Review, Revise Credits Final, Revise final sound
16	Final Film Submission					Final Film Submission